## Construction Projects
Project | BU | Location | Status | % | Value (RM) | VO/RM | CDS | SPP | Unit | Quantity | Average (RM/unit) | Award | MANAGERS | MABAGERS VALUES RM | Remark | Date (Last Follow up) | actual finish date | est. Finish date | day | Value Completed | finish date | Priority | Year
Marina Bay Towers | BU001 | Kuala Lumpur | Completed | 100 | 2500000 | 0 | 2023-01-01 | 0 | sqft | 50000 | 50 | Awarded | Ahmad Hassan | 2500000 | On schedule | 2024-11-30 | 2024-09-30 | 2024-10-01 | 45 | 2500000 | 2024-09-30 | High Priority | 2024
Green Park Complex | BU002 | Shah Alam | In Progress | 75 | 1800000 | 150000 | 2023-06-15 | 0 | sqft | 35000 | 51.43 | Awarded | Fatima Aziz | 1950000 | Minor delays | 2024-11-25 | 2024-11-15 | 2024-11-30 | 60 | 1350000 | 2024-11-15 | Medium Priority | 2024
Tech Hub Office | BU003 | Penang | On Hold | 45 | 5200000 | 300000 | 2023-03-20 | 150000 | sqft | 80000 | 65 | Pending | Raj Kumar | 5550000 | Awaiting approval | 2024-11-20 | 2024-12-20 | 2025-01-15 | 90 | 2340000 | 2024-12-20 | Low Priority | 2024
Riverside Residential | BU004 | Ipoh | Not Started | 0 | 3100000 | 0 | 2024-12-01 | 0 | sqft | 60000 | 51.67 | Tender Process | Siti Nuha | 3100000 | Procurement phase | 2024-11-28 | 2025-06-01 | 2025-06-15 | 180 | 0 | 2025-06-01 | Critical | 2025
Shopping District Mall | BU001 | Selangor | Completed | 100 | 950000 | 0 | 2022-09-10 | 0 | sqft | 25000 | 38 | Awarded | Mohan Singh | 950000 | Final inspection passed | 2024-11-15 | 2024-08-30 | 2024-09-05 | 30 | 950000 | 2024-08-30 | Completed | 2024
Industrial Port Zone | BU002 | Johor | In Progress | 60 | 4200000 | 200000 | 2023-08-05 | 100000 | acres | 15 | 280000 | Awarded | Chen Wei | 4500000 | Structural work ongoing | 2024-11-22 | 2025-03-15 | 2025-04-01 | 120 | 2520000 | 2025-03-15 | High Priority | 2025
Sports Arena Complex | BU003 | Melaka | On Hold | 30 | 6800000 | 500000 | 2022-11-12 | 250000 | sqft | 120000 | 56.67 | Under Review | Norazilah Ali | 7550000 | Awaiting permits | 2024-11-18 | 2025-07-01 | 2025-08-15 | 200 | 2040000 | 2025-07-01 | Medium Priority | 2025
Medical Center Building | BU004 | Kuala Lumpur | Not Started | 0 | 2200000 | 0 | 2024-11-15 | 0 | sqft | 45000 | 48.89 | Tender Process | Ahmad Hassan | 2200000 | Planning phase | 2024-11-25 | 2025-05-01 | 2025-05-20 | 150 | 0 | 2025-05-01 | High Priority | 2025
University Campus Phase 2 | BU001 | Shah Alam | Completed | 100 | 3500000 | 0 | 2021-05-01 | 0 | sqft | 75000 | 46.67 | Awarded | Fatima Aziz | 3500000 | All systems operational | 2024-11-27 | 2024-07-15 | 2024-08-01 | 28 | 3500000 | 2024-07-15 | Completed | 2024
Eco-Friendly Housing | BU002 | Penang | In Progress | 85 | 1600000 | 75000 | 2023-04-20 | 0 | units | 200 | 8000 | Awarded | Raj Kumar | 1675000 | Interior finishing | 2024-11-26 | 2024-12-10 | 2024-12-25 | 50 | 1360000 | 2024-12-10 | Medium Priority | 2024