## OCM Table
Project | BU | Location | Status | % | Value (RM) | Value Completed | VO(RM) | CDS | day | est. Finish date | Unit | Quantity | Average (RM/unit) | Award | Safuan | Hamdee | Woradate | Nantawat | Alya | Vignes | Azim | Remark | Date (Last Follow up)
Capacitor Bank An Xin Target 500RM TNB Bill reduce each month | Food | An Xin Kepong | On going | 100% | 6000 | 6000 | 0 | 3/28/2025 |  | NAT | unit | 1 | 6000 | NKM | [5 empty] | 6000 |  | Wait for TNB Approval | NAT
Water Supply 2inches PVC pipe est.50m | Farm | BRC2 | On going | 100% | 10500 | 10500 | 0 | 7/31/2025 |  | NAT | m | 50 | 210 | Kasas Plumbing | [5 empty] | 10500 |  | Wait for TNB Approval | NAT
Broilers 2houses 18x95x2.7m Finish 15/01/25 | Farm | BRC2 | On going | 100% | 1250000 | 1250000 | 3420 | 5/27/2025 |  | NAT | m2 | 3420 | 365.4971 | MKR |  |  | 1250000 |  |  |  |  | Wait for TNB Approval | NAT
Broilers 1houses 16x120x2.7m Finish 15/01/25 | Farm | BRC5 | On going | 100% | 645000 | 645000 | 14915 | 3/23/2025 |  | NAT | m2 | 1920 | 335.9375 | LLK |  |  | 645000 |  |  |  |  | not required | NAT
CCTV BIN Monitoring, 32 unit transport | Feed | BWF | On going | 100% | 63404 | 63404 |  | 10/31/2025 |  | NAT | No. | 32 | 1981.375 | Zheng Cheng |  | 63404 | [5 empty] | not required | NAT
CYF earthwork | Swine | Chau Yang Farm | On going | 100% | 430000 | 430000 | 157500 | 1/11/2025 |  | NAT | m3 | 16500 | 26.0606 | LNL Ent (Liew Eric) |  |  | 430000 |  |  |  |  | not required | NAT
Repairing Crack/ Big Gap Area Block 1 to Block 8 at Layer | Farm | Desaru | On going | 100% | 18000 | 18000 | 0 | 12/1/2025 |  | NAT | No. | 8 | 2250 | Pioneer | [5 empty] | 18000 |  | not required | NAT
Repairing Crack/ Big Gap Area Block 9 to Block 16 at Layer | Farm | Desaru | On going | 100% | 19900 | 19900 | 0 | 10/9/2025 |  | NAT | No. | 8 | 2487.5 | Pioneer | [5 empty] | 19900 |  | not required | NAT
Replace door and add urinal partition | Farm | Desaru | On going | 100% | 19810 | 19810 | 0 | 2/23/2025 |  | NAT | LS | 1 | 19810 | Pioneer | [5 empty] | 19810 |  | not required | NAT
Emergency repair due to Windstorm | Farm | Desaru | On going | 100% | 177031.5 | 177031.5 | 0 | 4/21/2025 |  | NAT | m2 | 5901 | 30.0003 | Pioneer |  |  | 177031.5 |  |  |  |  | After LV switchboard arrive, we can T&C | NAT
Fencing Manager House 91m | Farm | Desaru | On going | 100% | 28800 | 28800 |  | 11/8/2025 |  | NAT | m | 91 | 316.4835 | Southline Engineering | [5 empty] | 28800 |  | Pending meter deposit payment for complete shutdown and energizing new meter | NAT
Egg bay (liquid) | Farm | Desaru | On going | 100% | 15589.26 | 15589.26 |  | 11/7/2025 |  | NAT | m2 | 65 | 239.8348 | Pioneer | [5 empty] | 15589.26 |  | not required | NAT
OVERHAUL SERVICE & MAINTENANCE BIOGAS GENSET 1x600 kVA + New 12x Cylinder heads Assy | Farm | Desaru | completed | 100% | 50000 | 50000 |  | 1/25/2025 | 30 | 2025-03-26 | no. | 12 | 4166.6667 | Advance Energy | [5 empty] | 50000 |  | not required | NAT
Desaru2 Survey | Farm | Desaru2 | On going | 100% | 35640 | 35640 |  | 3/26/2025 |  | NAT | Acre | 400 | 89.1 | Mesra Ukur | [5 empty] | 35640 |  | not required | NAT
Water Tank 5,000 GL 4x4m2 Tank 48% Concrete 52% | Farm | Kluang Hatchery | On going | 100% | 22400 | 22400 |  | 8/22/2025 |  | NAT | m2 | 16 | 1400 | South Line Eng. | [5 empty] | 22400 |  | not required | NAT
Road repair | Farm | Kluang Hatchery | On going | 100% | 23820 | 23820 |  | 1/30/2025 |  | NAT | m2 | 96 | 248.125 | South Line Eng. | [5 empty] | 23820 |  | not required | NAT
Tubewell 12m3/hr Groundfos SP11-24 Motor MS4000 3phases | Farm | Kluang Farm | On going | 100% | 76000 | 76000 | 4000 | 7/10/2025 |  | NAT | m3/hr | 12 | 6333.3333 | MILLENIUM | [5 empty] | 76000 |  | Wait for TNB Approval | NAT
Solar roof 400kwp saving 115,000RM/year | Farm | Kluang Hatchery | On going | 100% | FOC | FOC | 0 | 9/16/2025 |  | NAT | LS | 1 | #VALUE! | Solarvest | [5 empty] | FOC |  | Wait for TNB Approval | NAT
Supply and install U drain 52m | Farm | Kluang Hatchery | On going | 100% | 140000 | 140000 |  | 1/13/2025 |  | NAT | m | 52 | 2692.3077 | You Fatt | [5 empty] | 140000 |  | Wait for TNB Approval | NAT
Renovation Hostel 12rooms | Farm | Kota Farm | On going | 100% | 245000 | 245000 |  | 4/25/2025 |  | NAT | no. | 12 | 20416.6667 | Pioneer | [5 empty] | 245000 |  | not required | NAT
Change PU Roofing Pedas 2 For House 3 Flock C 1,680m2 PK3 4house move from Pedas 2 by MKR cost 237,500RM | Farm | Kota Farm | On going | 100% | 45200 | 45200 |  | 3/5/2025 |  | NAT | m2 | 1680 | 26.9048 | Pioneer | [5 empty] | 45200 |  | not required | NAT
Kota TNB ( KM & BP for TNB only) 1,000A | Farm | Kota Hatchery | On going | 100% | 21600 | 21600 |  | 12/25/2025 |  | NAT | A | 1000 | 21.6 | TSK Enterprise | [5 empty] | 21600 |  | not required | NAT
Kota hatchery earthwork | Farm | Kota Hatchery | On going | 100% | 119500 | 119500 |  | 11/17/2025 |  | NAT | m2 | 2400 | 49.7917 | SZ Bumi | [5 empty] | 119500 |  | not required | NAT
Move and renovate Water treatment Tank from Pedas 2 to PK3 | Farm | PK3 | On going | 100% | 50500 | 50500 | 7500 | 8/29/2025 |  | NAT | LS | 1 | 50500 | BMS | [5 empty] | 50500 |  | not required | NAT
Add on packaging room (3.6m x 20m) | Farm | PK3 | On going | 100% | 32800 | 32800 |  | 7/29/2025 |  | NAT | m2 | 72 | 455.5556 | Kowitech | [5 empty] | 32800 |  | not required | NAT
Male Toilet interior 28m2 | Feed | PKF | On going | 100% | 150000 | 150000 | 12001 | 3/1/2025 |  | NAT | m2 | 28 | 5357.1429 | AIDEA |  |  | 150000 |  |  |  |  | After LV switchboard arrive, we can T&C | NAT
Repair concrete Feedmill 150m2 | Feed | PKF | On going | 100% | 124000 | 124000 |  | 7/14/2025 |  | NAT | m2 | 150 | 826.6667 | MKR | [5 empty] | 124000 |  | Pending meter deposit payment for complete shutdown and energizing new meter | NAT
CCTV BIN Monitoring, 48 unit transport | Feed | PKF | On going | 100% | 96800 | 96800 |  | 10/24/2025 |  | NAT | No. | 48 | 2016.6667 | Zheng Cheng |  | 96800 | [5 empty] | not required | NAT
Bin Stiffener 2 stiffener 24m | Feed | PKF | On going | 100% | 206000 | 206000 |  | 10/20/2025 |  | NAT | m | 24 | 8583.3333 | Omori |  |  | 206000 |  |  |  |  | not required | NAT
Change warehouse roof | Feed | PKF | On going | 100% | 110000 | 110000 | 16000 | 10/16/2025 |  | NAT | m2 | 1785 | 61.6246 | MKR | [5 empty] | 110000 |  | not required | NAT
PU Floor Extruder, 4mm BC Crete | Feed | PKF | On going | 100% | 60000 | 60000 |  | 12/6/2025 |  | NAT | m2 | 252 | 238.0952 | SealProof |  | 60000 | [5 empty] | not required | NAT
Changing room Premix | Feed | PKF | On going | 100% | 33692 | 33692 |  | 4/6/2025 |  | NAT | m2 | 40 | 842.3 | Kowitech | [5 empty] | 33692 |  | not required | NAT
Paver block beside silo 5 3days work on 23rd May | Feed | PKF | On going | 100% | 30800 | 30800 |  | 1/1/2025 |  | NAT | m2 | 40 | 770 | Kowitech | [5 empty] | 30800 |  | Wait for TNB Approval | NAT
Lift up loading bay | Feed | PKF | On going | 100% | 320000 | 320000 |  | 10/28/2025 |  | NAT | m2 | 40 | 8000 | MKR |  | 320000 | [5 empty] | Wait for TNB Approval | NAT
Mixer purchase 4 T/hr 130,000USD | Feed | PKF | On going | 100% | 585000 | 585000 |  | 1/8/2025 |  | NAT | T/hr | 4 | 146250 | Agrimate |  | 585000 | [5 empty] | Wait for TNB Approval | NAT
Tire Dipping (wheel Dipping) 3.5*4m2 | Feed | PKF | On going | 100% | 12500 | 12500 |  | 7/15/2025 |  | NAT | m2 | 14 | 892.8571 | Kowitech |  |  | 12500 |  |  |  |  | not required | NAT
Silo Panel Room (Electric room) 1.5*2m2 | Feed | PKF | On going | 100% | 15640 | 15640 |  | 3/4/2025 |  | NAT | m2 | 3 | 5213.3333 |  |  |  | 15025 |  |  |  |  | not required | NAT
Patching premix besides weight bridge 128m2 | Feed | PKF | On going | 100% | 15025 | 15025 |  | 10/10/2025 |  | NAT | m2 | 128 | 117.3828 |  |  |  | 15025 |  |  |  |  | not required | NAT
Dismantle H19 roof and install in H14 | Farm | Rantau | On going | 100% | 11000 | 11000 |  | 2/22/2025 |  | NAT | m2 | 1440 | 7.6389 | LLK | [5 empty] | 11030 |  | not required | NAT
Cement Board Ceiling and Septic Tank Installation | Farm | Kota | On going | 1.8% | 28000 | 504 |  | 12/30/2025 |  | NAT | m2 | 450 | 62.2222 | [7 empty] | 28000 | not required | 2025-10-11
Renovate Cooling pad 2houses | Farm | Sayong Farm | On going | 100% | -31000 | -31000 |  | 9/23/2025 |  | NAT | m2 | 194.5 | -159.383 | MNH | [5 empty] | -31000 |  | not required | NAT
Change roof 3,295m2 | Farm | Sayong Hatchery | On going | 100% | 235000 | 235000 |  | 6/9/2025 |  | NAT | m2 | 3295 | 71.3202 | Pioneer |  |  | 235000 |  |  |  |  | After LV switchboard arrive, we can T&C | NAT
Replace current 3 units air cooler at infeed room install July | Food | Senawang | completed | 100% | 275000 | 275000 |  | 9/24/2025 |  | 2025-08-06 | No. | 3 | 91666.6667 | Mayekawa | 275000 | [6 empty] | Pending meter deposit payment for complete shutdown and energizing new meter | NAT
Refurbish Screw Shaft and Filter Plates | Food | Senawang | On going | 100% | 41093.3333 | 41093.3333 |  | 9/21/2025 |  | NAT | LS | 1 | 41093.3333 | C.K.E.&S. TRADING (THAILAND) | 41093.3333 | [6 empty] | not required | NAT
Overhaul 2x MYCOM Screw compressor | Food | Senawang | On going | 100% | 56000 | 56000 |  | 10/30/2025 |  | NAT | No. | 2 | 28000 | Mayekawa | 56000 | [6 empty] | not required | NAT
Purchase Bun Slicing and Sauce Filling Machine for Sausage Roll and Burger | Food | Senawang | On going | 100% | 55000 | 55000 |  | 7/22/2025 |  | NAT | no. | 1 | 55000 | UKI Food Technology | 55000 | [6 empty] | not required | NAT
Purchase Horizontal Packing (Flow Wrap) for Sausage Roll and Burger Line | Food | Senawang | On going | 100% | 180000 | 180000 |  | 11/5/2025 |  | NAT | no. | 1 | 180000 | UKI Food Technology | 180000 | [6 empty] | not required | NAT
Installation Turn Table Machine for Sausage Roll and Burger Line | Food | Senawang | On going | 100% | 12800 | 12800 |  | 7/30/2025 |  | NAT | no. | 1 | 12800 | Omori | 12800 | [6 empty] | not required | NAT
Installation Transfer Conveyor Machine for Sausage Roll and Burger Line | Food | Senawang | On going | 100% | 15500 | 15500 |  | 8/26/2025 |  | NAT | no. | 1 | 15500 | Omori | 15500 | [6 empty] | comparison done | NAT
PM Compressor PK2 by MYCOM (Overhaul) | Food | Senawang | On going | 100% | 78216 | 78216 |  | 1/18/2025 |  | NAT | LS | 1 | 78216 | MYCOM | 78216 | [6 empty] | Fabrication process | NAT
Siput Hostel renovation | Farm | Sg Siput | On going | 100% | 60343 | 60343 |  | 11/30/2025 |  | NAT | m2 | 251 | 240.4104 | Sin sam Chuan | [5 empty] | 60343 |  | Fabrication process | NAT
Tubewell 12m3/hr Groundfos SP11-24 Motor MS4000 3phases | Farm | Sg Siput | On going | 100% | 73000 | 73000 |  | 10/29/2025 |  | NAT | m3/hr | 12 | 6083.3333 | GWS | [5 empty] | 73000 |  | Fabrication process | NAT
Purchase Electrical Cable Hs 1 | Farm | Sg Siput | On going | 100% | 50800 | 50800 |  | 11/17/2025 |  | NAT | m |  | #DIV/0! | Sin Sam Chuan | 50800 | [6 empty] | Fabrication process | NAT
Renovation Office, Store, Car Spray, Washing and Car Park | Farm | Tampin | On going | 100% | 195000 | 195000 |  | 4/29/2025 |  | NAT | m2 | 200 | 975 | Pioneer | [5 empty] | 195000 |  | Fabrication process | NAT
URGENT ORDER IINCIDENT REPORT SHENGDONG BIOGAS GENSET 2 ,alternater burn | Farm | Desaru | On going | 100% | 50000 | 50000 |  | 11/23/2025 |  | NAT | LS | 1 | 50000 | Advance Energy |  |  | 50000 |  |  |  |  | Fabrication process | NAT
Tubewell (12m3/hr) | Farm | PK2 | On going | 100% | 69000 | 69000 |  | 6/2/2025 |  | NAT | m3/hr | 12 | 5750 | GWS | [5 empty] | 69000 |  | Fabrication process | NAT
Wood Shaving ramp 15m3 concrete | Farm | Tampin | On going | 100% | 40500 | 40500 |  | 6/4/2025 |  | NAT | m3 | 15 | 2700 | Kowitech | [5 empty] | 40500 |  | Fabrication process | NAT
Tubewell (12m3/hr) | Farm | Sayong Farm | On going | 100% | 78000 | 78000 |  | 2/16/2025 |  | NAT | m3/hr | 12 | 6500 | MNK | [5 empty] | 78000 |  | Fabrication process | NAT
Rest pavillion for driver waiting area egg grading 3x3m2 ?? | Farm | Desaru | completed | 100% | 5000 | 5000 |  | 9/25/2025 |  | 2025-05-09 | m3 |  | #DIV/0! | South Line Eng. |  |  | 5000 |  |  |  |  | Fabrication process | NAT
Hostel ceiling repair | Farm | Kluang | On Going | 100% | 19500 | 19500 |  | 7/17/2025 |  | NAT | m2 | 70 | 278.5714 | M Shah | [5 empty] | 19500 |  | Fabrication process | NAT
REPAIR AIR COMPRESSOR #1 Model GX 5 P TM | Farm | Chengkau | On going | 100% | 4794 | 4794 |  | 4/3/2025 |  | NAT | unit | 1 | 4794 | ULTRA AIR INDUSTRIAL SUPPLIES | [5 empty] | 4794 |  | Fabrication process | NAT
REPAIR AIR COMPRESSOR #2 Model GX 5 P TM | Farm | Chengkau | On going | 100% | 3412 | 3412 |  | 2/25/2025 |  | NAT | unit | 1 | 3412 | ULTRA AIR INDUSTRIAL SUPPLIES | [5 empty] | 3412 |  | Fabrication process | NAT
Dismantle 1 House Roofing at Pedas 2 and Transport to Chengkau (Rent crane 3,560 RM) refer to 9 houses to Chengkau by Pioneer 78,000 RM 4 houses to PK3 w install 23,7500 RM | Farm | Chengkau | completed | 100% | 12210 | 12210 |  | 9/17/2025 | 7 | 2025-10-09 | House | 1 | 12210 | Pioneer | [5 empty] | 12210 |  | Fabrication process | NAT
Repair Motor and Pump | Farm | Chengkau | On going | 100% | 905 | 905 |  | 12/25/2025 |  | NAT | unit | 1 | 905 | NKM M&E | [5 empty] | 905 |  |  | NAT
Air Compressor 10HP 2units Hitachi with Dryer | Food | Sg Siput | On going | 100% | 26500 | 26500 |  | 1/29/2025 |  | NAT | Unit | 2 | 13250 | Airnergy | [7 empty] | TNB approval in process | NAT
Land survey to Apply business license 10 acres | Farm | BRC5 | On going | 100% | 3200 | 3200 |  | 2/7/2025 |  | NAT | acre | 10 | 320 | Jurukur Hartamas | [5 empty] | 3200 |  |  | NAT
Purchase Metal Detector Machine for Sausage Roll and Burger Line Metal Detector 63k + Rejector 23k + Local Reject Bin 3.5k- by Anritsu Offer 89.5kRM Final 75,000RM CIF Port Klang | Food | Senawang | On going | 100% | 88000 | 88000 |  | 1/14/2025 |  | NAT | no. | 1 | 88000 | Cairnhill Metrology (ANRITSU) | 88000 | [6 empty] | Wait for TNB Approval | NAT
TTM retrieving CCC documents | Food | TTM | On going | 100% | 500 | 500 |  | 3/10/2025 |  | NAT | LS | 1 | 500 | JPS | [5 empty] | 500 |  | Wait for TNB Approval | NAT
Chicken Stunner 88,000euro Install August | Food | Senawang | On going | 100% | 400000 | 400000 |  | 5/30/2025 |  | NAT | LS | 1 | 400000 | BAADER | 400000 | [6 empty] | Wait for TNB Approval | NAT
SUN COVER Louver COOLING PAD Louver 260m | Farm | Desaru | completed | 100% | 120000 | 120000 |  | 5/17/2025 |  | 2025-09-21 | m2 | 624 | 192.3077 | MKR | 120000 | [6 empty] | Wait for TNB Approval | NAT
CCTV BIN Monitoring, 32 unit Installation | Feed | BWF | On going | 100% | 66000 | 66000 |  | 8/4/2025 |  | NAT | No. | 32 | 2062.5 | Wattyll |  |  |  | 66000 |  |  |  | Wait for TNB Approval | NAT
Single Supplier Wastewater Pond BRC1 | Farm | BRC1 | completed | 100% | 37800 | 37800 |  | 9/14/2025 | 12 | 2025-10-11 | Day | 12 | 3150 | WT Tee | [5 empty] | 37800 |  | Wait for TNB Approval | NAT
Spot filter Bucket Elevator 10+6nos. | Feed | JHF | On going | 95% | 39000 | 37050 |  | 10/8/2025 |  | NAT | No. | 16 | 2437.5 | Soon Lian Engineering |  |  | 39000 |  |  |  |  | not required | NAT
Modify 2 hoppers Meal silo | Feed | JHF | On going | 95% | 39999 | 37999.05 |  | 8/23/2025 |  | NAT | No. | 2 | 19999.5 | AJ Peo Engineering |  |  | 39999 |  |  |  |  | not required | NAT
Kota Hatchery renovate Phase 0 and 1 1300m2 VO Spides & CC3 Fencing | Farm | Kota Hatchery | On going | 95% | 2760000 | 2622000 | 135680 | 2/24/2025 |  | NAT | m2 | 1300 | 2123.0769 | MKR |  |  | 2760000 |  |  |  |  | not required | NAT
Genset 500KVA supply (New) | Farm | Kota Hatchery | On going | 95% | 205000 | 194750 |  | 4/20/2025 |  | NAT | LS | 1 | 205000 | Advance Energy Engineering | [5 empty] | 205000 |  | not required | NAT
TNB Upgrade meter (contractor) | Farm | PK3 | On going | 95% | 28500 | 27075 |  | 10/13/2025 |  | NAT | A | 1200 | 23.75 | NKM | [5 empty] | 28500 |  | not required | NAT
An Xin Puchong Renovation | Food | An Xin Puchong | On going | 100% | 200000 | 200000 | 3872 | 3/31/2025 |  | NAT | m2 | 90.616 | 2207.1157 | Vintage Fareast | [5 empty] | 200000 |  | not required | NAT
Purchase air compressor Brand: Hitachi | Farm | Sg Siput | On going | 100% | 29200 | 29200 |  | 9/11/2025 |  | NAT | no. | 2 | 14600 | AIrnergy Sdn Bhd | 29200 | [6 empty] | After LV switchboard arrive, we can T&C | NAT
Water Treatment | Farm | Tampin | On going | 100% | 64000 | 64000 |  | 1/8/2025 | 30 | NAT | LS | 1 | 64000 | GWS | [5 empty] | 64000 |  | Pending meter deposit payment for complete shutdown and energizing new meter | NAT
TNB Upgrade meter (consultant) | Farm | PK3 | On going | 90% | 17000 | 15300 |  | 5/1/2025 |  | NAT | A | 1200 | 14.1667 | NKM | [5 empty] | 17000 |  | not required | NAT
Kota TNB (consultant) | Farm | Kota Hatchery | On going | 40% | 20000 | 8000 |  | 12/7/2025 |  | NAT | LS | 1 | 20000 | CTMEC | [5 empty] | 20000 |  | not required | NAT
TNB Chengkau (Consultant) | Farm | Chengkau | On going | 100% | 22099 | 22099 |  | 1/12/2025 |  | NAT | LS | 1 | 22099 | CTMEC | [5 empty] | 22099 |  | not required | NAT
Chengkau upgrade TNB 285m (VO Upgrade ATS 17k, Clearing land 44k, Rent Gen set 750kVA) | Farm | Chengkau | On going | 100% | 510000 | 510000 | 72600 | 11/3/2025 |  | NAT | m | 285 | 1789.4737 | RID | [5 empty] | 510000 |  | not required | NAT
Replace Line Sensor 45% and Generator 55% for X-Ray Further Plant 2 lead time 60days | Food | Senawang | completed | 100% | 62384.62 | 62384.62 |  | 6/17/2025 | 60 | 2025-08-31 | unit | 1 | 62384.62 | Ishida System | 62384.62 | [6 empty] | not required | NAT
Whole bird packing for line 1 & 3 Korea | Food | Senawang | completed | 80% | 1030000 | 824000 |  | 6/27/2025 |  | 2025-07-12 | LS | 1 | 1030000 | Multivac | 1030000 | [6 empty] | not required | NAT
Hostel and office renovation | Farm | Sayong Farm | completed | 100% | 133550 | 133550 |  | 10/31/2025 |  | 2025-11-15 | m2 |  | #DIV/0! | Pioneer | [5 empty] | 133550 |  | not required | NAT
Hostel and Toilet Renovation (Interior) | Farm | Sayong Hatchery | completed | 100% | 91450 | 91450 |  | 7/7/2025 |  | 2025-07-22 |  |  | #DIV/0! | Pioneer | [5 empty] | 91450 |  | not required | NAT
IQF 1,200 kg/hr Install October | Food | Senawang | On going | 70% | 1543014 | 1080109.8 |  | 7/18/2025 |  | NAT | Kg/hr | 1200 | 1285.845 | CP M&E China |  |  | 1543014 |  |  |  |  | not required | NAT
TNB Guard house | Swine | TTM | On going | 60% | 28500 | 17100 |  | 9/1/2025 |  | NAT | LS | 1 | 28500 | JSM Ventures | [5 empty] | 28500 |  | not required | NAT
Permit Generator 30 gensets 4-6 months | Farm | 11 location | On going | 60% | 55000 | 33000 |  | 6/6/2025 | 180 | NAT | no. | 30 | 1833.3333 | KAC | [5 empty] | 75000 |  | not required | NAT
Tubewell 2-4 sets ( total 30m3/hr) min. 8m3/hr | Swine | Chau Yang Farm | completed | 95% | 290000 | 275500 |  | 9/10/2025 | 30 | 2025-10-25 | m3/hr | 30 | 9666.6667 | GWS | [5 empty] | 290000 |  | not required | NAT
TTM Land Survey | Swine | TTM | On going | 50% | 10000 | 5000 |  | 12/20/2025 |  | NAT | acre | 100 | 100 | Geodatum | [5 empty] | 10000 |  | not required | NAT
Water Treatment | Farm | Kota Farm | completed | 60% | 64000 | 38400 |  | 12/4/2025 | 30 | 2026-01-18 | LS | 1 | 64000 | GWS | [5 empty] | 64000 |  | Arrange for VO bottom tapper | NAT
Desaru Hostel 12rooms | Farm | Desaru | On going | 45% | 695000 | 312750 |  | 8/23/2025 |  | NAT | m2 | 356 | 1952.2472 | WIldstone |  |  | 695000 |  |  |  |  | Arrange for VO bottom tapper | NAT
Breeder House size 14 x 126 x 2.7 House 17,18,19 By equipment 3.6M | Farm | Rantau | On going | 70% | 2520000 | 1764000 |  | 2/20/2025 |  | NAT | m2 | 5040 | 500 | LLK | [5 empty] | 2520000 |  | Arrange for VO bottom tapper | NAT
Permit KM&BP Lot 20420 (Port Dickson) | Farm | Rantau | On going | 50% | 129600 | 64800 |  | 3/31/2025 |  | NAT | LS | 1 | 129600 | LJH PROJECT MANAGEMENT | [5 empty] | 129600 |  | Arrange for VO bottom tapper | NAT
Permit KM&BP Lot 106 (Rendering) S | Food | Senawang | On going | 20% | 118000 | 23600 |  | 8/18/2025 |  | NAT | LS | 1 | 118000 | LJH PROJECT MANAGEMENT |  | 118000 | [5 empty] | Arrange for VO bottom tapper | NAT
PM Compressor PK1, IQF by MYCOM | Food | Senawang | On going | 20% | 62439 | 12487.8 |  | 11/27/2025 |  | NAT | LS | 1 | 62439 | MYCOM |  | 62439 | [5 empty] | Arrange for VO bottom tapper | NAT
Permit KM&BP Lot 1587 Tampin (Repah) | Farm | Tampin | On going | 50% | 129600 | 64800 |  | 7/13/2025 |  | NAT | LS | 1 | 129600 | LJH PROJECT MANAGEMENT | [5 empty] | 129600 |  | Arrange for VO bottom tapper | NAT
Live pig weighing scale w platform 1x1.8m2 H=1.2m Ichida scale cost 12k RM | Swine | TTM | On going | 30% | 66156.2 | 19846.86 |  | 1/12/2025 |  | NAT | m2 | 1.2 | 55130.1667 | Mettler Toledo | [5 empty] | 66156.2 |  | Arrange for VO bottom tapper | NAT
Hostel, Bathroom and Toilet Renovation 4000m2 | Swine | TTM | On Going | 20% | 300000 | 60000 |  | 5/14/2025 |  | NAT | m2 | 4000 | 75 | BYself | [5 empty] | 300000 |  | Arrange for VO bottom tapper | NAT
Permit KM&BP Lot 32575 & 32575 (Slaughter & FPP1) S | Food | Senawang | On going | 20% | 135000 | 27000 |  | 7/11/2025 |  | NAT | LS | 1 | 135000 | LJH PROJECT MANAGEMENT |  | 135000 | [5 empty] | Arrange for VO bottom tapper | NAT
Flake Ice Machine at primary plant 20T/day | Food | Senawang | On going | 20% | 320000 | 64000 | 0 | 3/4/2025 |  | NAT | T/days | 20 | 16000 | Ice-Tech Regrigeration |  |  | 320000 |  |  |  |  | Arrange for VO bottom tapper | NAT
CCTV BIN Monitoring, 48 unit Installation | Feed | PKF | On going | 10% | 104000 | 10400 |  | 11/1/2025 |  | NAT | No. | 48 | 2166.6667 | Wattyll |  |  |  | 104000 |  |  |  | Arrange for VO bottom tapper | NAT
Silo 3600T | Feed | PKF | On going | 25% | 1800000 | 450000 |  | 10/10/2025 |  | NAT | Ton | 3600 | 500 | Chuan Ho |  |  | 1800000 |  |  |  |  | Arrange for VO bottom tapper | NAT
6 units 5000 gallon water tank 8x12.5m2 | Farm | Sayong Farm | On Going | 30% | 127000 | 38100 |  | 8/6/2025 |  | NAT | m2 | 100 | 1270 | Pioneer | [5 empty] | 127000 |  | Arrange for VO bottom tapper | NAT
HVAC Kota Hatchery M&E 1,300m2 | Farm | Kota Hatchery | completed | 75% | 1700000 | 1275000 |  | 3/24/2025 | 75 | 2025-06-22 | m2 | 1300 | 1307.6923 | IPC |  |  |  | 1700000 |  |  |  | Arrange for VO bottom tapper | NAT
Kluang TNB 1,800A Consultant | Farm | Kluang | On Going | 5% | 20000 | 1000 |  | 10/17/2025 |  | NAT | A | 1800 | 11.1111 | PTAG | [5 empty] | 20000 |  | Arrange for VO bottom tapper | NAT
G1-Awning loading bay 3x12 | Farm | Desaru | completed | 5% | 13285 | 664.25 |  | 1/3/2025 | 30 | 2025-02-17 | m2 | 18 | 738.0556 | Berjasa | 13285 | [6 empty] | Arrange for VO bottom tapper | NAT
G1-Replace Roof Separator (1 Lot) | Farm | Desaru | completed | 5% | 4700 | 235 |  | 12/21/2025 | 30 | 2026-02-04 | m2 | 39 | 120.5128 | Southline | 4700 | [6 empty] | Arrange for VO bottom tapper | NAT
Breeder House size 14 x 126 x 2.7 House 17,18,19 By equipment 3.6M | Farm | Rantau | On going | 2% |  | 0 |  | 7/4/2025 |  | NAT | m2 | 40 | 0 | BD | [7 empty] | Arrange for VO bottom tapper | NAT
Kota TNB ( contractor) 1,000A LV Cable (eAuction) | Farm | Kota Hatchery | On going | 5% | 456000 | 22800 |  | 10/26/2025 |  | NAT | m | 250 | 1824 | RID | [5 empty] | 456000 |  | Arrange for VO bottom tapper | NAT
IWK System 100PE | Farm | Desaru | completed | 15% | 275000 | 41250 |  | 3/29/2025 | 120 | 2025-08-11 | PE | 100 | 2750 | Innovate Engineering | [5 empty] | 275000 |  | Arrange for VO bottom tapper | NAT
Biogas B4 12,000m3 Linning & Cover Biogas B5 6,000m3 Linning only | Swine | Chau Yang Farm | completed | 2% | 1190000 | 23800 |  | 7/19/2025 | 105 | 2025-11-16 | m3 | 12000 | 99.1667 | GTEK |  |  | 1190000 |  |  |  |  | Arrange for VO bottom tapper | NAT
New submain cabling & Change over panel (Biogas to Egg grading panel) AUTOCHANGER FOR AHU EGG GRADING Pantavanij | Farm | Desaru | completed | 10% | 129500 | 12950 |  | 4/26/2025 | 60 | 2025-07-10 | LS | 1 | 129500 | RID | [5 empty] | 129500 |  | Arrange for VO bottom tapper | NAT
Office/canteen TTM concrete roof waterproof 14x47m | Swine | TTM | completed | 2% | 63183 | 1263.66 |  | 4/29/2025 | 45 | 2025-06-28 | m2 | 658 | 96.0228 | BET |  |  | 63183 |  |  |  |  | Arrange for VO bottom tapper | NAT
G1-Renovate floor for store room (replace mozac) 20'x24' | Farm | Desaru | completed | 2% | 11771.3 | 235.426 |  | 6/26/2025 | 30 | 2025-08-10 | m2 | 43.2 | 272.4838 | MKR | 11771.3 | [6 empty] | Arrange for VO bottom tapper | NAT
G1-Replace Roof Genset 1 (7.7x8.7) | Farm | Desaru | completed | 2% | 11050 | 221 |  | 6/14/2025 | 30 | 2025-07-29 | m2 | 66.99 | 164.95 | Southline | 11000 | [6 empty] | Arrange for VO bottom tapper | NAT
Chain Feeder H4(6 loops) and H5(6 loops) minus some part in farm stock 8,468RM not include installation/ lead time 3 months | Farm | Kota Farm | completed | 2% | 230000 | 4600 |  | 8/11/2025 |  | 2025-08-26 | Loops | 10 | 23000 | Big Dutchman |  |  | 230000 |  |  |  |  | Arrange for VO bottom tapper | NAT
Slat for Broiler 800x600 BRC2 3000 pcs | Farm | BRC2 | completed | 2% | 78500 | 1570 |  | 7/8/2025 |  | 2025-07-23 | m2 | 1920 | 40.8854 | Big Dutchman |  |  | 78500 |  |  |  |  | Arrange for VO bottom tapper | NAT
Slat for Broiler 800x600 BRC6 3000 pcs | Farm | BRC6 | completed | 2% | 78500 | 1570 |  | 3/14/2025 |  | 2025-03-29 | m2 | 1920 | 40.8854 | Big Dutchman |  |  | 78500 |  |  |  |  | Arrange for VO bottom tapper | NAT
Replace egg conveyor parts (2weeks) | Farm | Desaru | completed | 2% | 235000 | 4700 |  | 4/1/2025 |  | 2025-04-16 | LS | 1 | 235000 | Big Dutchman |  |  | 235000 |  |  |  |  | Arrange for VO bottom tapper | NAT
Mini chiller 2x Ascon 112,600 R410A Inverter BTU 10 weeks | Farm | Sg Siput | completed | 2% | 53960 | 1079.2 |  | 9/8/2025 | 30 | 2025-10-23 | Unit | 2 | 26980 | Mai Nichi | 53960 | [6 empty] | Arrange for VO bottom tapper | NAT
Egg Packer | Farm | Desaru | On going | 2% | 700000 | 14000 |  | 8/14/2025 |  |  | unit | 1 | 700000 | Mai Nichi |  |  | 700000 |  |  |  |  | Arrange for VO bottom tapper | NAT
Egg lift elevator eggsmart (8weeks) | Farm | PK3 | completed | 2% | 612000 | 12240 |  | 8/24/2025 | 60 | 2025-11-07 | unit | 1 | 612000 | Mai Nichi |  |  | 612000 |  |  |  |  | Arrange for VO bottom tapper | NAT
Water tank 1,000GLx5 5,000GLx5 10,000GLx1 (Weida Poly tank same chicken farm Average 4-5rm/gallon not include concrete platform) | Swine | Chau Yang farm | completed | 10% | 90100 | 9010 |  | 4/16/2025 | 21 | 2025-05-22 | Gallon | 40000 | 2.2525 | Sin Sam Suan | [5 empty] | 90100 |  | not required | NAT
Aerator 15kW Water Treatment, not include earthwork 2 pond 24x24x3.5m included SST | Swine | Chau Yang Farm | completed | 2% | 262000 | 5240 |  | 11/18/2025 | 150 | 2026-05-02 | kw | 15 | 17466.6667 | Viro (Midori) |  |  | 262000 |  |  |  |  | not required | NAT
Setia Alam Permit | Account | Setia Alam | completed | 90% | 3000 | 2700 |  | 6/19/2025 |  |  |  |  | #DIV/0! | [6 empty] | 3000 |  | not required | NAT
Zoning - Land title before KM/BP Lot 970 & 971 (Labu) | Farm | Labu | completed | 5% | 33264 | 1663.2 |  | 1/28/2025 | 180 | 2025-08-11 | lot | 2 | 16632 | Segaris Ukur Konsultant Sdn Bhd | [5 empty] | 33264 |  | not required | NAT
KLUANG REFIT BIOGAS MAN ENGINE 250Kw 99,510THB | Farm | Kluang | completed | 90% | 13268 | 11941.2 |  | 9/3/2025 | 30 | 2025-10-18 | LS | 1 | 13268 | The Golden Line | 13268 | [6 empty] | not required | NAT
Replace Chiller Bio-Gas Gen 1 | Farm | Desaru | On going | 3% | 31000 | 930 |  | 10/25/2025 | 30 | NAT | no. | 1 | 31000 | MTC TEchnics | 31000 | [6 empty] | not required | NAT
Genset 500KVA (Replace) | Farm | BRC1 | Tendering | 1.8% | 250000 | 4500 |  | 9/18/2025 |  | NAT | KVA | 500 | 500 | MTC TEchnics | [5 empty] | 250000 |  | not required | NAT
Genset 500KVA (Replace) | Farm | BRC2 | Tendering | 1.8% | 250000 | 4500 |  | 1/30/2025 |  | NAT | KVA | 500 | 500 | MTC TEchnics | [5 empty] | 250000 |  | not required | NAT
Genset 500KVA (Replace) | Farm | Renggam | Tendering | 1.8% | 250000 | 4500 |  | 2/8/2025 |  | NAT | KVA | 500 | 500 | MTC TEchnics | [5 empty] | 250000 |  | not required | NAT
Genset 500KVA (Replace) | Farm | Sedili | Tendering | 1.8% | 250000 | 4500 |  | 8/20/2025 |  | NAT | KVA | 500 | 500 | MTC TEchnics | [5 empty] | 250000 |  | not required | NAT
Dismantle existing Incubator 9 Setters & 9 Hatchers Dismantle chiller & re-install | Farm | Kota Hatchery | Tendering | 1.8% | 30000 | 540 |  | 1/2/2025 |  | NAT | unit | 15 | 2000 | MTC TEchnics | [5 empty] | 30000 |  | not required | NAT
PU Floor Hatchery 248m2 | Farm | Sayong Hatchery | completed | 2% | 54000 | 1080 |  | 12/6/2025 | 14 | 2026-01-04 | m2 | 248 | 217.7419 | Trion Industrial | [5 empty] | 54000 |  | not required | NAT
Fire Wall 320m2 | Feed | JHF | On going | 2% | 200000 | 4000 |  | 7/21/2025 |  |  | m2 | 320 | 625 |  |  |  | 200000 |  |  |  |  | Waiting tender by pantavanij | NAT
Fencing Lagoon for biogas 100m(L) x 3m(H) | Farm | Desaru | completed | 2% | 35000 | 700 |  | 12/24/2025 | 30 | 2026-02-07 | m | 100 | 350 | M Shah | 35000 | [6 empty] | Waiting tender by pantavanij | NAT
New Control room | Feed | BWF | Tendering | 1.5% | 300000 | 4500 |  | 6/25/2025 | 60 |  | m2 | 31.45 | 9538.9507 | [5 empty] | 300000 |  |  | Pre tender by 2/10/2025 | NAT
Mixer upgrade to 4 T/hr Installation (ex. Electric) | Feed | PKF | completed | 100% | 175000 | 175000 | 5654 | 10/4/2025 | 3 | 2025-10-07 | T/hr | 4 | 43750 | Chuan Ho | 175000 | [6 empty] | VO for buy softstarter | NAT
Breeder House size 14 x 150 x 2.7 total 4 houses , Equipment 4.8M | Farm | Sayong Farm | completed | 2% | 4400000 | 88000 |  | 5/31/2025 | 150 | 2025-11-12 | m2 | 8400 | 523.8095 | MKR |  |  | 4400000 |  |  |  |  | VO for buy softstarter | NAT
Main Conveyor 3 Unit | Farm | PK3 | Tendering | 1.5% | 2100000 | 31500 |  | 5/30/2025 |  | NAT | m2 | 8400 | 250 |  |  |  | 2100000 |  |  |  |  | VO for buy softstarter | NAT
MORILLON PARTS 50k USD + KPI Supervisor 12k USD | Feed | JHF | Tendering | 1.5% | 279000 | 4185 |  | 5/17/2025 |  | NAT |  | 8400 | 33.2143 | KPI |  |  | 279000 |  |  |  |  | VO for buy softstarter | NAT
Redo Door Works For Layer Chicken House | Farm | Desaru | Tendering | 1.2% | 72000 | 864 |  | 5/16/2025 |  | NAT | no. | 8400 | 8.5714 | KPI |  |  | 72000 |  |  |  |  | VO for buy softstarter | NAT
Renovate canteen, Surau and Toilet | Farm | Chengkau | On Going | 2% | 30000 | 600 |  | 4/13/2025 | 30 | NAT | m2 | 8400 | 3.5714 | KPI | [5 empty] | 30000 |  | tender on 10/11/2025 | NAT
6 Unit Hostel and Toilet Renovate | Farm | Chengkau | On Going | 2% | 50000 | 1000 |  | 4/24/2025 | 60 | NAT | m2 | 8400 | 5.9524 | KPI | [5 empty] | 50000 |  | tender on 10/11/2025 | NAT
Main egg conveyor phase 1, 4 1 unit | Farm | Desaru | Tendering | 1% | 700000 | 7000 |  | 11/14/2025 |  | NAT | m | 8400 | 83.3333 | KPI |  |  | 700000 |  |  |  |  | tender on 10/11/2026 | NAT
Capacitor Bank An Xin | Food | An Xin Meranti | On going | 100% | 6000 | 6000 |  | 7/17/2025 |  | NAT | no. | 1 | 6000 | KPI | [5 empty] | 6000 |  | tender on 10/11/2027 | NAT
An Xin SS15 Renovation for meat showcase 2.88m2 | Food | An Xin SS15 | Tendering | 1% | 6500 | 65 |  | 11/18/2025 |  | NAT | m2 | 2.88 | 2256.9444 | KPI |  |  | 6500 |  |  |  |  | tender on 10/11/2028 | NAT
Slope protection | Farm | Chengkau | On going | 2% | 114000 | 2280 |  | 12/30/2025 |  | NAT | m3 | 2.88 | 39583.3333 | KPI |  |  | 114000 |  |  |  |  | tender on 10/11/2029 | NAT
Chimney dust collector | Feed | JHF | Tendering | 1% | 220000 | 2200 |  | 8/16/2025 |  | NAT |  | 2.88 | 76388.8889 | KPI |  |  | 220000 |  |  |  |  | tender on 10/11/2030 | NAT
Capacitor Bank An Xin | Food | An Xin Taman Aman | On going | 100% | 6000 | 6000 |  | 10/30/2025 |  | NAT |  | 2.88 | 2083.3333 | KPI | [5 empty] | 6000 |  | tender on 10/11/2031 | NAT
Kota Hatchery Renovation phase 2-3 internal work | Farm | Kota | Tendering | 1% | 1600000 | 16000 |  | 11/23/2025 |  | NAT | m2 | 1350 | 1185.1852 | KPI |  |  | 1600000 |  |  |  |  | tender on 10/11/2032 | NAT
Kota TNB ( contractor) 1,000A HDD Cable | Farm | Kota Hatchery | Designing | 1% | 1000000 | 10000 |  | 1/6/2025 |  | NAT | m | 100 | 10000 | KPI | [5 empty] | 1000000 |  | tender on 10/11/2033 | NAT
Renovate Roof and Engineering Office 8x16 | Feed | PKF | Tendering | 1% | 400000 | 4000 |  | 4/26/2025 |  | NAT | m2 | 128 | 3125 | KPI |  |  | 400000 |  |  |  |  | tender on 10/11/2034 | NAT
Renovate canteen, Surau and Toilet 8x18 | Feed | PKF | Tendering | 1% | 400000 | 4000 |  | 12/24/2025 |  | NAT | m2 | 144 | 2777.7778 | KPI |  |  | 400000 |  |  |  |  | tender on 10/11/2035 | NAT
Breeder House size 14 x 126 x 2.7 House 7,8,9 By 31 October 2025 equipment 3.6M | Farm | Rantau | Tendering | 1% | 3000000 | 30000 |  | 4/21/2025 |  | NAT | m2 | 1512 | 1984.127 | KPI |  |  | 3000000 |  |  |  |  | tender on 10/11/2036 | NAT
Genset 750KVA (Replace) | Farm | Rantau | Tendering | 1% | 500000 | 5000 |  | 5/12/2025 |  | NAT | KVA | 1 | 500000 | KPI | [5 empty] | 500000 |  | tender on 10/11/2037 | NAT
Genset 750KVA (Replace) | Farm | Sayong Farm | Tendering | 1% | 500000 | 5000 |  | 1/2/2025 |  | NAT | KVA | 750 | 666.6667 | KPI | [5 empty] | 500000 |  | tender on 10/11/2038 | NAT
TTM Fire store room 9x8.5 | Food | TTM | Tendering | 1% | 260000 | 2600 |  | 11/27/2025 |  | NAT | m2 | 76.5 | 3398.6928 | KPI |  |  | 260000 |  |  |  |  | tender on 10/11/2039 | NAT
Desaru Packer 600,000 eggs/day (NABEL 2 units) | Farm | Desaru | Tendering | 1% | 1254000 | 12540 |  | 6/27/2025 |  | NAT |  | 76.5 | 16392.1569 | KPI | [6 empty] | 1254000 | not required | NAT
Land survey to Apply business license | Farm | Sayong Farm | Tendering | 1% | 50000 | 500 |  | 9/9/2025 |  | NAT |  | 76.5 | 653.5948 | KPI | [5 empty] | 50000 |  | not required | NAT
Feed Cleaner CPM 6036 38,001USD -> 34,000USD CFR PKF | Feed | PKF | On going | 2% | 146200 | 2924 |  | 9/29/2025 |  | NAT | Unit | 1 | 146200 | KPI |  |  | 146200 |  |  |  |  | not required | NAT
Premix from intake, Mixer to packing 9T/days | Feed | PKF | Designing | 0.8% | 200000 | 1600 |  | 2/23/2025 |  | NAT |  |  |  | CPM |  |  |  | 200000 |  |  |  | not required | NAT
Broiler OEM 8 houses x 30,000 Birds | Farm | Yong Peng | Tendering | 1% | 17000000 | 170000 |  | 1/20/2025 |  | NAT | Birds | 240000 | 70.8333 | CPM |  |  | 17000000 |  |  |  |  | not required | NAT
Bird counter by SensorHaus 400,000THB in Thailand | Food | Senawang | Tendering | 1% | 60000 | 600 |  | 2/27/2025 |  | NAT | LS | 1 | 60000 | CPM | [7 empty] | not required | NAT
Fire Fighting System in PKF 1st phase of 3 phase | Feed | PKF | Tendering | 1% | 300000 | 3000 |  | 4/15/2025 |  | NAT | LS | 1 | 300000 | CPM |  |  | 300000 |  |  |  |  | not required | NAT
IQF 1,200 kg/hr Foundation | Food | Senawang | Tendering | 1% | 50000 | 500 |  | 8/18/2025 |  | NAT | m2 | 1 | 50000 | CPM |  |  | 50000 |  |  |  |  | not required | NAT
Sampling roof | Feed | BWF | Designing | 0.9% | 1000000 | 9000 |  | 9/29/2025 |  | NAT | m2 | 1 | 1000000 | CPM |  |  | 1000000 |  |  |  |  | not required | NAT
Guard House | Farm | PK2 | Designing | 0.9% | 10000 | 90 |  | 11/26/2025 |  | NAT | m2 | 1 | 10000 | CPM | 10000 | [6 empty] | not required | NAT
Manager House | Farm | PK2 | Designing | 0.9% | 100000 | 900 |  | 8/17/2025 |  | NAT | m2 | 1 | 100000 | CPM | 100000 | [6 empty] | not required | NAT
Kluang TNB 1,800A MV TNB to Transformer | Farm | Kluang | Designing | 0.8% | 2000000 | 16000 |  | 7/4/2025 |  | NAT | m | 1300 | 1538.4615 | CPM | [5 empty] | 2000000 |  | not required | NAT
Kluang TNB Fencing BRC 30m/run | Farm | Kluang | Tendering | 1.8% | 9000 | 162 |  | 11/25/2025 |  | NAT |  | 1300 | 6.9231 | CPM | [7 empty] | not required | NAT
Kluang BRC Fencing TNB 30m/run | Farm | Kluang | On going | 80% | 9000 | 7200 |  | 9/3/2025 |  | NAT | m | 30 | 300 | CPM | [5 empty] | 9000 |  | not required | NAT
Kluang TNB 1,800A HDD to TNB | Farm | Kluang | Designing | 0.8% | 400000 | 3200 |  | 6/25/2025 |  | NAT | m | 300 | 1333.3333 | CPM | [5 empty] | 400000 |  | not required | NAT
New office est. 138m2 | Farm | Desaru | Designing | 0.8% | 200000 | 1600 |  | 7/1/2025 |  | NAT | m2 | 138 | 1449.2754 | CPM |  |  | 380000 |  |  |  |  | not required | NAT
Storage Room Egg Grading (12 x 7 m) | Farm | Desaru | Designing | 0.8% | 26000 | 208 |  | 7/28/2025 |  | NAT | m2 | 138 | 188.4058 | CPM |  |  | 26000 |  |  |  |  | not required | NAT
Divert water washing farm to water pond | Farm | Kluang Farm | Designing | 0.8% | 273155 | 2185.24 |  | 7/11/2025 |  | NAT | m | 138 | 1979.3841 | CPM |  |  | 273155 |  |  |  |  | not required | NAT
G1 - 10HP aircond for coldroom x 2 units | Farm | Sayong Hatchery | Tendering | 1.2% | 70000 | 840 |  | 2/28/2025 |  | NAT |  | 138 | 507.2464 | CPM | [7 empty] | Pending quotation from Sui Yuen | NAT
G1 - 10HP aircond for Setter and Hatcher x 2 units | Farm | Sayong Hatchery | Tendering | 1.2% | 92000 | 1104 |  | 4/20/2025 |  | NAT |  | 138 | 666.6667 | CPM | [7 empty] | Pending quotation from Sui Yuen | NAT
Hatchery Chain Link Fencing 260m | Farm | Sayong Hatchery | completed | 2% | 24148.5 | 482.97 |  | 3/9/2025 | 30 | 2025-04-23 | m | 260 | 92.8788 | Pioneer | [5 empty] | 24148.5 |  | Pending PRPO CDS | 2025-10-08
New TNB Set & Auto Genset | Farm | PK2 | Tendering | 1.2% | 100000 | 1200 |  | 3/9/2025 |  | NAT | m2 | 260 | 384.6154 | Pioneer |  |  |  | 100000 |  |  |  | Pending PRPO CDS | NAT
Biogas Sludge cleaning | Farm | Kluang | Designing | 0.6% | 59000 | 354 |  | 6/11/2025 |  | NAT | LS | 260 | 226.9231 | Pioneer |  |  | 59000 |  |  |  |  | Pending PRPO CDS | NAT
UrgeNT ORDER Repair Roof damage 18x21 | Farm | Sayong Hatchery | completed | 90% | 68000 | 61200 |  | 11/25/2025 | 45 | 2026-01-24 | m2 | 378 | 179.8942 | Pioneer | [7 empty] | Pending PRPO CDS | NAT
PU Floor 4mm thick PU MF 1050 m2 | Farm | Kuala Kangsar | Tendering | 1.8% | 200000 | 3600 |  | 4/3/2025 |  | NAT | m2 | 1050 | 190.4762 | Pioneer | [5 empty] | 200000 |  | Arrange for pre-tender | 30/10/2025
An Xin Cheras Yulek 4.5x12m2 | Food | An Xin Cheras | Designing | 0.5% | 184750 | 923.75 |  | 4/8/2025 |  | NAT | m2 | 54 | 3421.2963 | Pioneer | [5 empty] | 184750 |  | Arrange for pre-tender | 30/10/2026
Renovate Office | Feed | BWF | Designing | 0.5% | 210000 | 1050 |  | 5/24/2025 |  | NAT | m2 | 54 | 3888.8889 | not required |  |  | 210000 |  |  |  |  | Arrange for pre-tender | 30/10/2027
To supply only excavator long arm and manpower for open lagoon | Farm | Kluang Farm | Designing | 0.5% | 30000 | 150 |  | 2/12/2025 |  | NAT | m3 | 54 | 555.5556 | not required |  |  | 30000 |  |  |  |  | Arrange for pre-tender | 30/10/2028
Supply machinery for excavate 2 units water pond {Pond 1: 50m x 100m x 4m (D) , Pond 2 : 25m x 100m x 4m(D)} | Farm | Kluang Farm | Designing | 0.5% | 200000 | 1000 |  | 8/31/2025 |  | NAT | m3 | 30000 | 6.6667 | not required |  |  | 200000 |  |  |  |  | Arrange for pre-tender | 30/10/2029
Kota Hatchery Renovation phase 4 external work | Farm | Kota Hatchery | Designing | 0.5% | 400000 | 2000 |  | 3/8/2025 |  | NAT | m2 | 30000 | 13.3333 | not required |  |  | 400000 |  |  |  |  | Arrange for pre-tender | 30/10/2030
To supply and build 1 unit new car spray {Size: 5m (W) x 15m (L) x 4.5m(H) } Q2 | Farm | Kota Hatchery | Designing | 0.5% | 150000 | 750 |  | 2/16/2025 |  | NAT | m2 | 30000 | 5 | not required | [5 empty] | 150000 |  | Arrange for pre-tender | 30/10/2031
Renovate control room | Feed | PKF | Designing | 0.5% | 300000 | 1500 |  | 12/5/2025 | 60 | NAT | m2 | 90 | 3333.3333 | not required |  |  |  |  | 300000 |  |  | Arrange for pre-tender | 30/10/2032
Coffee Stall 3.6x5.3 (Five star coffee) | Food | UPM | Designing | 0.5% | 110000 | 550 |  | 7/12/2025 | 30 | NAT | m2 | 38.16 | 2882.5996 | not required |  |  |  |  | 110000 |  |  | Arrange for pre-tender | 30/10/2033
Roof 16x26m2 for Centralised Silo 18T 4sets | Swine | Chau Yang Farm | Designing | 0.5% | 400000 | 2000 |  | 2/16/2025 | 30 | NAT | m2 | 416 | 961.5385 | not required |  |  |  |  | 400000 |  |  | Arrange for pre-tender | 30/10/2034
G1-Chemical Room follow requirement DVS & JKKP 5x6m2 | Farm | Desaru | Designing | 0.5% | 20000 | 100 |  | 10/19/2025 |  | NAT | m2 | 30 | 666.6667 | not required |  |  | 20000 |  |  |  |  | Arrange for pre-tender | 30/10/2035
CYF Fencing 2,110m and drainage 1,030m | Swine | Chau Yang Farm | Tendering | 1% | 2550000 | 25500 |  | 1/30/2025 |  | NAT | m | 2200 | 1159.0909 | not required |  |  | 2550000 |  |  |  |  | Arrange for pre-tender | 30/10/2036
Office & Spray Room 10x30m2 + 6x15m2 | Swine | Chau Yang Farm | Designing | 0.3% | 900000 | 2700 |  | 2/23/2025 |  | NAT | m2 | 390 | 2307.6923 | not required |  |  | 900000 |  |  |  |  | Arrange for pre-tender | NAT
Renovation Spray Vehicle & 10x Spray Room Entrance | Farm | Rantau | Designing | 0.8% | 50000 | 400 |  | 4/25/2025 |  | NAT | m2 | 390 | 128.2051 | not required | [6 empty] | 50000 | Arrange for pre-tender | NAT
Guard House Renovation | Farm | Sayong | Designing | 0.8% | 20000 | 160 |  | 11/2/2025 |  | NAT | LS | 390 | 51.2821 | not required | [6 empty] | 20000 | Arrange for pre-tender | NAT
Hot water Boiler Biogas 500L tank+500k Diesel burner ( 2 contractors only) | Farm | Desaru | Designing | 0.1% | 80000 | 80 |  | 5/12/2025 |  | NAT | LS | 1 | 80000 | not required | 80000 | [6 empty] | Arrange for pre-tender | NAT
G2-Improvement Sand Trap for bio-gas | Farm | Desaru | Tendering | 1% | 100000 | 1000 |  | 1/1/2025 |  | NAT | LS | 1 | 100000 | not required | 100000 | [6 empty] | Arrange for pre-tender | NAT
Office Renovation | Farm | Rantau | Designing | 0.1% | 100000 | 100 |  | 1/5/2025 |  | NAT | m2 | 1 | 100000 | not required | [6 empty] | 100000 | Arrange for pre-tender | NAT
Warehouse Bird Net | Feed | PKF | Designing | 0.05% | 180000 | 90 |  | 8/16/2025 |  | NAT | m2 | 460 | 391.3043 | not required |  |  | 180000 |  |  |  |  | Arrange for pre-tender | NAT
Concrete Paving Work at Dump Egg Grading | Farm | Desaru | Designing | 0% | 10000 | 0 |  | 7/14/2025 |  | NAT | m2 | 460 | 21.7391 | not required |  |  | 10000 |  |  |  |  | Arrange for pre-tender | NAT
Hostel Extension | Farm | Kota Farm | Designing | 0.3% | 32000 | 96 |  | 7/12/2025 |  | NAT | m2 | 460 | 69.5652 | not required |  |  |  | 32000 |  |  |  | Arrange for pre-tender | NAT
Silo Roof Exhaust Fan D102-D105 | Feed | PKF | On going | 100% | 22000 | 22000 |  | 1/6/2025 |  | NAT | m3 | 36 | 611.1111 | Omori | 22000 | [6 empty] | not required | NAT
2nd Bin Stiffener 3 stiffener 36m | Feed | PKF | On going | 2% | 307506 | 6150.12 |  | 5/20/2025 |  | NAT | m | 36 | 8541.8333 | Omori |  |  | 307506 |  |  |  |  | not required | NAT
Modified Bin Cover for CCTV | Feed | PKF | On going | 100% | 19960 | 19960 |  | 1/21/2025 |  | NAT | pcs | 40 | 499 | KH Maju | 19960 | [6 empty] | not required | NAT
500 KW Biogas Generator | Swine | Chau Yang Farm | Tendering | 1% |  | 0 |  | 2/24/2025 |  | NAT | pcs | 41 | 0 | KH Maju | [6 empty] | 0 | not required | NAT
Conveyor after mixer 100T/hr L= 7.5m | Feed | PKF | Designing | 0.5% | 55704 | 278.52 |  | 3/4/2025 |  | NAT | pcs | 42 | 1326.2857 | KH Maju | 55704 | [6 empty] | not required | NAT
BD for preventive maintenance and replacement , focusing on houses 5 to 8 and replacement cages at house 7 Spare parts H5-8 810,000 MYR Replacement cages H7 150,000 MYR Lead time was confirmed as 5 weeks for cage replacement and 3 weeks per house for preventive maintenance, with a completion target by mid-November to avoid extended repair delays | Farm | Desaru | completed | 2% | 960000 | 19200 |  | 2025-10-17 | 35 | 2025-12-06 | Hoses | 4 | 240000 | Big Dutchman |  |  | 960000 |  |  |  |  | not required | NAT
PKF Silo Senior Site Agent 2 months | Feed | PKF | completed | 50% | 18000 | 9000 |  | 2025-09-07 | 60 | 2025-11-21 | Months | 2 | 9000 | Sinarunding | [7 empty] | not required | NAT
New staff house Q3 | Farm | Kota Farm | Designing | 1% | 300000 | 3000 |  | 11/27/2025 |  | NAT | m2 | 3 | 100000 | Sinarunding | [6 empty] | 300000 | not required | NAT
Warehouse 700m2 | Food | Senawang | Tendering | 1% | 1800000 | 18000 |  | 4/24/2025 |  | NAT | m2 | 4 | 450000 | Sinarunding |  |  | 1800000 |  |  |  |  | not required | NAT
Lab Renovation | Food | Senawang | Designing | 0.2% | 150000 | 300 |  | 11/1/2025 |  | NAT | m2 | 5 | 30000 | Sinarunding |  |  | 150000 |  |  |  |  | not required | NAT
Sachet Dispensor Sauce Pack- frying line Korean SKU 540pkt/hr to 2,700pkt/hr (by MT Food) | Food | Senawang | Designing | 0.1% | 670000 | 670 |  | 9/30/2025 |  | NAT | T/hr | 6 | 111666.6667 | Sinarunding |  |  | 670000 |  |  |  |  | not required | NAT
G2-Renovate Spray shower room 1 unit | Farm | Desaru | Designing | 0.1% | 30000 | 30 |  | 9/26/2025 |  | NAT | m2 | 7 | 4285.7143 | Sinarunding | 30000 | [6 empty] | not required | NAT
G2-Replace chicken dunk pipe to V shape concrete drainage to lagoon | Farm | Desaru | Designing | 0% | 100000 | 0 |  | 5/15/2025 |  | NAT | m | 8 | 12500 | Sinarunding |  |  | 100000 |  |  |  |  | Pending quotation from Sui Yuen | NAT
Main road fencing (use old zink from H3 Tampin & H3 Kota) Q2 | Farm | Kota Farm | Designing | 0% | 100000 | 0 |  | 9/11/2025 |  | NAT | m2 | 9 | 11111.1111 | Sinarunding | [6 empty] | 100000 | Pending quotation from Sui Yuen | NAT
Asphalt road Q4 | Farm | Kota Hatchery | Designing | 0% | 100000 | 0 |  | 7/12/2025 |  | NAT | m2 | 10 | 10000 | Sinarunding | [6 empty] | 100000 | Pending PRPO CDS | NAT
Improve Bomba system | Swine | TTM | Designing | 0% | 150000 | 0 | 0 | 6/2/2025 |  | NAT | m3 | 11 | 13636.3636 | Sinarunding | [6 empty] | 150000 | Pending PRPO CDS | NAT
Toilet Renovation | Farm | Sayong Hatchery | On Going | 2% | 20000 | 400 |  | 12/1/2025 |  | NAT | m4 | 12 | 1666.6667 | M shah | [6 empty] | 20000 | Pending PRPO CDS | NAT
Pelletizer | Feed | PKF | Tendering | 1% |  | 0 |  | 10/25/2025 |  | NAT | LS | 1 | 0 | M shah | 0 | [6 empty] | Pending PRPO CDS | NAT
SBM 3000T concrete silo | Feed | PKF | Designing | 0.5% | 15000000 | 75000 |  | 10/16/2025 |  | NAT | Ton | 3000 | 5000 | M shah |  |  | 15000000 |  |  |  |  | Arrange for pre-tender | NAT
PU floor Hatchery 380m2 | Farm | Sg Siput | Tendering | 1.8% | 100000 | 1800 |  | 10/25/2025 |  | NAT | m2 | 380 | 263.1579 | M shah | [6 empty] | 100000 | Arrange for pre-tender | NAT
Tampin & Hi-Voltage TNB over the land | Farm | Tampin | Designing | 0.5% | 30000 | 150 |  | 3/5/2025 |  | NAT | LS | 1 | 30000 | M shah | [7 empty] | Arrange for pre-tender | NAT
Boiler Economizer | Feed | Butterworth | Tendering | 1% | 250000 | 2500 |  | 10/7/2025 |  | NAT | Unit | 1 | 250000 | M shah | 250000 | [6 empty] | not required | NAT
Office Renovation | Farm | Rantau | Designing | 0.8% | 200000 | 1600 |  | 1/29/2025 |  | NAT | Unit | 2 | 100000 | M shah | [6 empty] | 200000 | not required | NAT
Permit KM&BP Port Klang Feedmill | Feed | PKF | Designing | 0.5% | 200000 | 1000 |  | 5/27/2025 |  | NAT | Unit | 3 | 66666.6667 | M shah | 200000 | [6 empty] | not required | NAT
IWK CYF 80PE | Swine | Chau Yang Farm | Designing | 1% | 500000 | 5000 |  | 8/14/2025 |  | NAT | Unit | 4 | 125000 | M shah | [6 empty] | 500000 | not required | NAT
Upgrade TNB | Feed | PKF | Designing | 0% |  | 0 |  | 2/14/2025 |  | NAT | Unit | 5 | 0 | M shah | [7 empty] | not required | NAT
Feather meal - Rendering cooker 1,600kg | Food | Senawang | Tendering | 1% | 2600000 | 26000 |  | 7/16/2025 |  | NAT | Unit | 6 | 433333.3333 | M shah | [7 empty] | not required | NAT
New Staff House 1 unit | Farm | PK2 | Designing | 0% | 100000 | 0 |  | 8/8/2025 |  | NAT | m2 | 7 | 14285.7143 | M shah | 100000 | [6 empty] | not required | NAT
Renovate Office 1 Unit | Farm | PK2 | Designing | 0% | 150000 | 0 |  | 11/23/2025 |  | NAT | m2 | 8 | 18750 | M shah | 150000 | [6 empty] | not required | NAT
Renovate Car Spray | Farm | PK2 | Designing | 0% | 15000 | 0 |  | 10/18/2025 |  | NAT | m2 | 9 | 1666.6667 | M shah | 15000 | [6 empty] | not required | NAT
Fencing With Zink | Farm | PK2 | Designing | 0% | 60000 | 0 |  | 11/11/2025 |  | NAT | m2 | 10 | 6000 | M shah | 60000 | [6 empty] | not required | NAT
New Store 1 unit (2 sections storage & chemical) | Farm | PK2 | Designing | 0% | 30000 | 0 |  | 11/3/2025 |  | NAT | m2 | 11 | 2727.2727 | M shah | 30000 | [6 empty] | not required | NAT
New lighting Line in Chicken House | Farm | PK2 | Designing | 0% | 40000 | 0 |  | 7/13/2025 |  | NAT | m2 | 12 | 3333.3333 | M shah | 40000 | [6 empty] | not required | NAT
New water Nipple Line 1 | Farm | PK2 | Designing | 0% | 60000 | 0 |  | 11/16/2025 |  | NAT | m2 | 13 | 4615.3846 | M shah | 60000 | [6 empty] | not required | NAT
CCTV Farm & Office | Farm | PK2 | Designing | 0.15% | 60000 | 90 |  | 8/10/2025 |  | NAT | m2 | 14 | 4285.7143 | M shah | 60000 | [6 empty] | Pending quotation from Sui Yuen | NAT
New Fan 1 Set | Farm | PK2 | Designing | 0.15% | 100000 | 150 |  | 8/10/2025 |  | NAT | m2 | 15 | 6666.6667 | Big Dutchman | 100000 | [6 empty] | Pending quotation from Sui Yuen | NAT
Renovate Office | Farm | PK3 | Designing | 0% | 200000 | 0 |  | 5/2/2025 |  | NAT | m2 | 16 | 12500 | Big Dutchman | 200000 | [6 empty] | Pending PRPO CDS | NAT
Renovate Car Spray 1 Unit | Farm | PK3 | Designing | 0% | 20000 | 0 |  | 7/24/2025 |  | NAT | m2 | 17 | 1176.4706 | Big Dutchman | 20000 | [6 empty] | Pending PRPO CDS | NAT
Renovate Manager House | Farm | PK3 | Designing | 0% | 30000 | 0 |  | 10/20/2025 |  | NAT | m2 | 18 | 1666.6667 | Big Dutchman | 30000 | [6 empty] | Pending PRPO CDS | NAT
Renovate Staff Hostel | Farm | PK3 | Designing | 0% | 100000 | 0 |  | 8/31/2025 |  | NAT | m2 | 19 | 5263.1579 | Big Dutchman | 100000 | [6 empty] | Pending PRPO CDS | NAT
New Store | Farm | PK3 | Designing | 0% | 50000 | 0 |  | 3/30/2025 |  | NAT | m2 | 20 | 2500 | Big Dutchman | 50000 | [6 empty] | Arrange for pre-tender | NAT
Store for Keep boat | Farm | PK3 | Designing | 0% | 10000 | 0 |  | 4/17/2025 |  | NAT | m2 | 21 | 476.1905 | Big Dutchman | 10000 | [6 empty] | Arrange for pre-tender | NAT
Container Roof | Farm | PK3 | Designing | 0% | 12000 | 0 |  | 6/15/2025 |  | NAT | m2 | 22 | 545.4545 | Big Dutchman | 12000 | [6 empty] | Arrange for pre-tender | NAT
New Egg Grading Roof | Farm | PK3 | Designing | 0% | 100000 | 0 |  | 8/23/2025 |  | NAT | m2 | 23 | 4347.8261 | Big Dutchman | 100000 | [6 empty] | not required | NAT
Mostor Mixer Pond Sumarin | Farm | PK3 | Designing | 0% | 140000 | 0 |  | 10/31/2025 |  | NAT | m2 | 24 | 5833.3333 | Big Dutchman | 140000 | [6 empty] | not required | NAT
Air Conditioner 10HP for Grading | Farm | PK3 | Designing | 0% | 60000 | 0 |  | 4/13/2025 |  | NAT | m2 | 25 | 2400 | Big Dutchman | 60000 | [6 empty] | not required | NAT
CCTV Grading | Farm | PK3 | Designing | 0% | 30000 | 0 |  | 7/6/2025 |  | NAT | m2 | 26 | 1153.8462 | Big Dutchman | 30000 | [6 empty] | not required | NAT
Biogas chiller | Farm | PK3 | Designing | 0% | 60000 | 0 |  | 9/22/2025 |  | NAT | m2 | 27 | 2222.2222 | Big Dutchman | 60000 | [6 empty] | not required | NAT
Biogas UPS | Farm | PK3 | Designing | 0% | 60000 | 0 |  | 2/19/2025 |  | NAT | m2 | 28 | 2142.8571 | Big Dutchman | 60000 | [6 empty] | not required | NAT
Improvement Sandtrap 1 unit | Farm | PK3 | Designing | 0% | 100000 | 0 |  | 7/26/2025 |  | NAT | m2 | 29 | 3448.2759 | Big Dutchman | 100000 | [6 empty] | not required | NAT
Hostel and Toilet Renovation | Farm | Sayong Hatchery | Designing | 0% | 100000 | 0 |  | 11/4/2025 |  | NAT | m2 | 30 | 3333.3333 | Big Dutchman | [6 empty] | 100000 | not required | NAT
Office and Canteen Renovate | Farm | Sayong Hatchery | Designing | 0% | 50000 | 0 |  | 8/7/2025 |  | NAT | m2 | 31 | 1612.9032 | Big Dutchman | [6 empty] | 50000 | not required | NAT
Thermoforming Retrofity by Multivac | Food | Senawang | Designing | 0% | 75565 | 0 |  | 8/4/2025 |  | NAT | no. | 1 | 75565 | Big Dutchman |  | 75565 | [5 empty] | not required | NAT
Cold Room 10 HP AC | Farm | Sayong Hatchery | On Going | 2% | 57800 | 1156 |  | 7/4/2025 |  | NAT | HP | 10 | 5780 | Mai-Nichi | [6 empty] | 57800 | not required | NAT
Hatchery and Setter 10HP AC | Farm | Sayong Hatchery | On Going | 2% | 41600 | 832 |  | 8/22/2025 |  | NAT | HP | 11 | 3781.8182 | Mai-Nichi | [6 empty] | 41600 | not required | NAT
Warehouse Roof Ridge Ventilator Dismantle, Fabrication and Installation | Feed | BWF | Designing | 0% | 81600 | 0 |  | 11/14/2025 |  | NAT | HP | 12 | 6800 | Mai-Nichi | [7 empty] | not required | NAT
Guard House Renovation | Farm | Sayong Farm | Tendering | 1.6% | 20000 | 320 |  | 3/24/2025 |  | NAT | HP | 13 | 1538.4615 | Mai-Nichi | [6 empty] | 20000 | Pending quotation from Sui Yuen | NAT
Incoming Electrical Supply H17-H19 | Farm | Rantau | Designing | 0.2% | 50000 |  |  | 1/19/2025 |  | NAT | HP | 14 | 3571.4286 | Mai-Nichi | [7 empty] | Pending quotation from Sui Yuen | NAT
Renovate Toilet(12' x 13') Pending KM | Farm | Desaru | Designing | 0% | 20000 | 0 |  | 8/8/2025 |  | NAT | m2 |  | #DIV/0! | Pioneer |  |  | 20000 |  |  |  |  | Pending PRPO CDS | NAT
Desaru 2 500,000Birds 2Pullets +8Layers Equipment 65% Building 35% | Farm | Desaru2 | Designing | 0.1% | 42488000 | 42488 | 0 | 8/8/2025 |  | NAT | Birds | 500000 | 84.976 | Pioneer | [5 empty] | 42488000 |  | Pending PRPO CDS | NAT
Consultant Desaru2 | Farm | Desaru2 | Tendering | 0.5% | 200000 | 1000 |  | 4/2/2025 |  | NAT | m2 | 500001 | 0.4 | Pioneer | [6 empty] | 200000 | Arrange for pre-tender | NAT
Site Clearing | Farm | Desaru2 | Tendering | 0.5% | 525000 | 2625 |  | 4/24/2025 |  | NAT | m2 | 500002 | 1.05 | Pioneer | [6 empty] | 525000 | Arrange for pre-tender | NAT
CYF 1500 Sows | Swine | Chau Yang Farm | Tendering | 1.2% | 49000000 | 588000 |  | 7/7/2025 |  | NAT | Sows | 1500 | 32666.6667 | Pioneer | [5 empty] | 49000000 |  | Arrange for pre-tender | NAT
SAJ (Water supply) | Farm | Renggam | Tendering | 1% | 150000 | 1500 |  | 9/5/2025 |  | NAT | LS | 1 | 150000 | Pioneer | [6 empty] | 150000 | not required | NAT
Renovate Cooling pad 6houses | Farm | Sayong Farm | Cancel | 5% | 153000 | 7650 |  | 3/5/2025 |  | NAT | m2 | 583.5 | 262.2108 | Pioneer | [6 empty] | 153000 | not required | NAT
Tubewell (12m3/hr) | Farm | BRC2 | On going | 35% | 74500 | 26075 | 4000 | 6/2/2025 |  | NAT | m3/hr | 12 | 6208.3333 | Millenium | [6 empty] | 74500 | not required | NAT
CCTV BIN Monitoring, 48 unit Installation | Feed | JHF | Tendering | 0.5% | 150000 | 750 |  | 4/4/2025 |  | NAT | m4/hr | 13 | 11538.4615 | Wattyl | 150000 | [6 empty] | not required | NAT
CCTV BIN Monitoring, 48 unit transport | Feed | JHF | Tendering | 0.2% | 148770.2435 | 297.5405 |  | 7/4/2025 |  | NAT | No. | 14 | 1836.6697 | CP M&E | 148770.2435 | [6 empty] | not required | NAT
PKF Pre-mixing production line | Feed | PKF | Designing | 0.2% | 2000000 | 4000 |  | 8/29/2025 |  | NAT | Set | 81 | 2000000 | CP M&E | 2000000 | [6 empty] | not required | NAT
SAJ (Water supply) | Farm | Renggam | Tendering | 1% | 150000 | 1500 |  | 7/12/2025 |  | NAT | LS | 1 | 150000 | CP M&E | [6 empty] | 150000 | not required | NAT
Fire protection system to get Bomba CCC | Farm | Renggam | Tendering | 1% | 500000 | 5000 |  | 1/21/2025 |  | NAT | LS | 1 | 500000 | CP M&E | [6 empty] | 500000 | not required | NAT
Manager House Renovation | Farm | Chengkau | Tendering | 1% | 30000 | 300 |  | 12/3/2025 |  | NAT | m2 | 2 | 15000 | CP M&E | [6 empty] | 30000 | not required | NAT
Formulas:
est. Finish date = [CDS]+30+[day]
est. Finish date = [CDS]+[day]+15
Note on H143: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Softstarter for main motor

## Summary
Summary project on hand, 2025
month | Design | Tender | Constuction | Value of tender
Jan | 0 | 5 | 1 | 331000
Feb | 0 | 6 | 2 | 2424874
Mar | 0 | 3 | 1 | 125000
Apr | 1 | 1 | 2 |  | Canteen Port klang , Hopper Johor, An Xin Subang, Dormitory Desaru
May | 7 | 2 | 7
Jun | 7 | 6 | 10
Jul | 16 | 15 | 13 | 2880874
Aug | 16 | 15 | 13 | 2880874
Aug (est.) | 18 | 20 | 15 | 2880874
General Affairs OCM 01/2025
No. | KM&BP | CCC | FIre Certificate | Cerificate Worker Hostel | Total
Tendering | 11 | 0 | 0 | 0 | 11
Designing | 0 | 11 | 3 | 20 | 34
Total(no.) | 11 | 11 | 3 | 20 | 45
OCM 01/2025
No. | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Finished | Under Construction |  | Value (RM) | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Progress | %Remain
Construction | 8 | 21 | 3 | 1 | 33 | 4 | 29 |  | Construction | 829203 | 6907251 | 703469 | 400000 | 8839923 | 4844919 | 45.19%
Tendering | 7 | 11 | 1 | 1 | 20 |  |  |  | Tendering | 2740000 | 2505500 | 1400000 | 49000000 | 55645500
Designing | 5 | 8 | 0 | 1 | 14 |  |  |  | Designing | 2170000 | 51858000 |  | 503000 | 54531000
Total(no.) | 20 | 40 | 4 | 3 | 67 |  |  |  | Total(RM) | 5739203 | 61270751 | 2103469 | 49903000 | 119016423
OCM 02/2025
No. | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Finished | Under Construction |  | Value (RM) | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Progress | %Remain
Construction | 8 | 20 | 3 | 2 | 33 | 14 | 19 |  | Construction | 829203 | 6879185 | 703469 | 428500 | 8840357 | 4844919 | 45.2%
Tendering | 7 | 13 | 1 | 1 | 22 |  |  |  | Tendering | 2980000 | 11784066 | 1400000 | 49000000 | 65164066
Designing | 5 | 24 | 2 | 2 | 33 |  |  |  | Designing | 2170000 | 48164600 | 25000000 | 503000 | 75837600
Total(no.) | 20 | 57 | 6 | 5 | 88 |  |  |  | Total(RM) | 5979203 | 66827851 | 27103469 | 49931500 | 149842023
OCM 03/2025
No. | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Finished | Under Construction |  | Value (RM) | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Progress | %Remain
Construction | 9 | 24 | 6 | 2 | 41 | 17 | 24 |  | Construction | 949203 | 7202825 | 1999093 | 428500 | 10579621 | 6582420 | 37.78%
Tendering | 6 | 12 | 2 | 3 | 23 |  |  |  | Tendering | 2850800 | 11726566 | 3225261 | 49212000 | 67014627
Designing & Consulting | 5 | 40 | 2 | 3 | 50 |  |  |  | Designing | 2180000 | 50273675 | 25150000 | 840000 | 78443675
Total(no.) | 20 | 76 | 10 | 8 | 114 |  |  |  | Total(RM) | 5980003 | 69203066 | 30374354 | 50480500 | 156037923
OCM 04/2025
No. | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Finished | Under Construction |  | Value (RM) | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Progress | %Remain
Construction | 10 | 32 | 8 | 2 | 52 | 19 | 33 |  | Construction | 922895 | 8196414 | 2074093 | 428500 | 11621902 | 7278791 | 37.37%
Tendering | 5 | 8 | 6 | 5 | 24 |  |  |  | Tendering | 2630800 | 10908600 | 4041481 | 49227000 | 66807881
Designing & Consulting | 4 | 37 | 2 | 3 | 46 |  |  |  | Designing | 2160000 | 50212575 | 25150000 | 840000 | 78362575
Total(no.) | 19 | 77 | 16 | 10 | 122 |  |  |  | Total(RM) | 5713695 | 69317589 | 31265574 | 50495500 | 156792358
OCM 05/2025
No. | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Finished | Under Construction |  | Value (RM) | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Progress | %Remain
Construction | 12 | 35 | 14 | 2 | 63 | 24 | 39 |  | Construction | 1273695 | 10749214 | 2547048 | 458500 | 15028457 | 10449856 | 30.47%
Tendering | 3 | 19 | 2 | 7 | 31 |  |  |  | Tendering | 2120000 | 10100600 | 3225261 | 49681500 | 65127361
Designing & Consulting | 4 | 33 | 3 | 2 | 42 |  |  |  | Designing | 1910000 | 49899555 | 25225565 | 290000 | 77325120
Total(no.) | 19 | 87 | 19 | 11 | 136 |  |  |  | Total(RM) | 5303695 | 70749369 | 30997874 | 50430000 | 157480938
OCM 06/2025
No. | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Finished | Under Construction |  | Value (RM) | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Progress | %Remain
Construction |  |  |  |  | 74 | 33 | 41 |  | Construction |  |  |  |  | 0 | 10449856 | #DIV/0!
Tendering |  |  |  |  | 0 |  |  |  | Tendering |  |  |  |  | 0
Designing & Consulting |  |  |  |  | 0 |  |  |  | Designing |  |  |  |  | 0
Total(no.) | 0 | 0 | 0 | 0 | 74 |  |  |  | Total(RM) | 0 | 0 | 0 | 0 | 0
OCM 07/2025
No. | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Finished | Under Construction |  | Value (RM) | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Progress | %Remain
Construction | 16 | 47 | 19 | 4 | 86 | 43 | 43 |  | Construction | 3671060 | 11567714 | 4616562 | 1224656 | 21079992 | 11641362 | 44.78%
Tendering | 8 | 30 | 3 | 4 | 45 |  |  |  | Tendering | 1870000 | 11337835 | 1814000 | 2624500 | 17646335
Designing & Consulting | 5 | 67 | 7 | 4 | 83 |  |  |  | Designing | 1990000 | 14771355 | 25830315 | 3740000 | 46331670
Total(no.) | 29 | 144 | 29 | 12 | 214 |  |  |  | Total(RM) | 7531060 | 37676904 | 32260877 | 7589156 | 85057997
OCM 08/2025
No. | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Finished | Under Construction |  | Value (RM) | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Progress | %Remain
Construction | #REF! | #REF! | #REF! | #REF! |  | 0 |  |  | Construction | #REF! | #REF! | #REF! | #REF! |  | 400
Tendering | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Tendering | #REF! | #REF! | #REF! | #REF!
Designing & Consulting | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Designing | #REF! | #REF! | #REF! | #REF!
Total(no.) | [8 empty] | Total(RM)
OCM 09/2025
No. | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Finished | Under Construction |  | Value (RM) | Feed Business | Farm & Integration | Food Business | Swine Business | Total | Progress | %Remain
Construction | 19 | 80 | 21 | 9 | 129 | 71 | 58 |  | Construction | 3871860 | 16373352.06 | 4705446.9533 | 2429939.2 | 27380598.2133 | 15885392.0903 | 41.98%
Tendering | 10 | 26 | 5 | 0 | 41 |  |  |  | Tendering | 2650004.5 | 33730000 | 384000 | 0 | 36764004.5
Designing & Consulting | 4 | 25 | 2 | 4 | 35 |  |  |  | Designing | 1690000 | 5660155 | 294750 | 4150000 | 11794905
Total(no.) | 33 | 131 | 28 | 13 | 205 |  |  |  | Total(RM) | 8211864.5 | 55763507.06 | 5384196.9533 | 6579939.2 | 75939507.7133
Column1 | Jan-25 | Feb-25 | Mac-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25
Construction Complete | 4 | 14 | 17 | 19 | 24 | 33 | 43 | 55 | 71
Construction Ongoing | 29 | 19 | 24 | 33 | 39 | 41 | 43 | 49 | 58
Tendering | 20 | 23 | 23 | 24 | 31 | 37 | 45 | 43 | 41
Designing | 14 | 50 | 50 | 46 | 42 | 55 | 83 | 62 | 35
Total | 67 | 106 | 114 | 122 | 136 | 166 | 214 | 209 | 205
[8 empty] | Total Value(RM) | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01
[8 empty] | Construction done | 4844919 | 4844919 | 6582420 | 7278791 | 10449856 | 11045609 | 11641362 | 13107978.1383 | 15885392.0903
[8 empty] | Construction Ongoing | 3995004 | 3995438 | 3997201 | 4343111 | 4578601 | 7008615.5 | 9438630 | 9968493.3919 | 11495206.123
[8 empty] | Tendering | 55645500 | 65164066 | 67014627 | 66807881 | 65127361 | 61386848 | 17646335 | 25909685.4762 | 36764004.5
[8 empty] | Designing | 54531000 | 75837600 | 78443675 | 78362575 | 77325120 | 81828395 | 46331670 | 27679321.4286 | 11794905
[8 empty] | Total | 119016423 | 149842023 | 156037923 | 156792358 | 157480938 | 161269467.5 | 85057997 | 76665478.4349 | 75939507.7133
Average (RM/project) | Dec-24
Construction Complete | 428164.1765
Construction Ongoing | 180962.9583
Tendering | 2904690.4783
Designing | 1567251.5